## Slide 1
CONTENT PLAN & BOOST BUDGET · W26–W28 · JUNE–JULY 2026
Tito AI
@TitoAIPH
3 weeks · 9 posts · Php 6,000 total · Launch Jun 22, 2026
Week 1 W26
Jun 22–28
Boost: TikTok only
Week 2 W27
Jun 29–Jul 5
Boost: TikTok + IG
Week 3 W28
Jul 6–12
Boost: All 3 platforms
TOTAL BUDGET
Php 6,000
LAUNCH DATE
Jun 22, 2026
PURPOSE
Followers + Views
Tito AI @TitoAIPH · Content Boost Plan · W26–W28 · June–July 2026
1

## Slide 2
Target Market — Mga Pamangkin
Everyday Filipinos · Age 22–45 · Philippines · Taglish-speaking
"The warm, relatable Tito who teaches everyday Filipinos to use AI — for free — before it replaces their job."
FREELANCERS
1.5M+ in PH (PIDS)
Fear: clients will replace them with AI. Need: faster proposals, better outputs, competitive edge.
GURO / TEACHERS
900K+ DepEd public school
Fear: curriculum disruption. Need: lesson plans in 2 min, grading, parent communication. One guro → 40 families.
BPO WORKERS
1.9M employees (BSP 2025)
Fear: automation layoffs. Need to upskill NOW — fastest-adopting segment for AI education content.
NANAYS / TATAYS
Millions of Filipino parents
Fear: being left behind. Need: family budgeting, homework help, meal planning, household productivity.
SME OWNERS
Only 14.9% use AI tools
Fear: losing to AI-enabled competition. Need: marketing, customer service, operations automation.
Tito AI @TitoAIPH · Content Boost Plan · W26–W28 · June–July 2026
2

## Slide 3
3-Week Boost Strategy
Post all platforms every week · boost budget ramps progressively · Php 2,000/week · launch Jun 22
WEEK 1 — W26
Jun 22–28
Boost: TikTok
MON Jun 22 · Ang Sabi Nila: Pang-Matalino
WED Jun 25 · Gemini para sa Guro
FRI Jun 27 · 1 Buwan Kasama Tito AI
Post organically to all platforms. Boost TikTok only — learn Promote mechanics and establish baseline CPV + CPF.
Php 2,000
WEEK 2 — W27
Jun 29–Jul 5
Boost: TikTok + IG
MON Jun 30 · July Teaser
WED Jul 2 · TBD — Wednesday Demo
FRI Jul 4 · TBD — Friday Story
Post organically to all platforms. Add Instagram Boost using W26 data to decide budget split.
Php 2,000
WEEK 3 — W28
Jul 6–12
Boost: All 3
MON Jul 7 · TBD — Monday AI Tip
WED Jul 9 · TBD — Wednesday Demo
FRI Jul 11 · TBD — Friday Story
Post organically to all platforms. Full boost across TikTok, IG, and Facebook. ⚠️ FB Page required.
Php 2,000
Tito AI @TitoAIPH · Content Boost Plan · W26–W28 · June–July 2026
3

## Slide 4
9-Post Content Calendar
Mon / Wed / Fri · drop 7–8 PM PHT · boost starts morning after posting
Week · Date
Topic
Platform
Budget
W26 · Jun 22
MON · Ang Sabi Nila: Pang-Matalino Lang Iyan
TikTok
Php 700
W26 · Jun 25
WED · Gemini para sa Guro
TikTok
Php 700
W26 · Jun 27
FRI · 1 Buwan Kasama Tito AI — Ang Resulta
TikTok
Php 600
W27 · Jun 30
MON · July Teaser — Ano ang Susunod?
TikTok
Php 700
W27 · Jul 2
WED · TBD — Wednesday Demo
Instagram
Php 700
W27 · Jul 4
FRI · TBD — Friday Story
TikTok
Php 600
W28 · Jul 7
MON · TBD — Monday AI Tip
TikTok
Php 600
W28 · Jul 9
WED · TBD — Wednesday Demo
Facebook
Php 800
W28 · Jul 11
FRI · TBD — Friday Story
Instagram
Php 600
9 posts · 3 weeks
Php 6,000
Tito AI @TitoAIPH · Content Boost Plan · W26–W28 · June–July 2026
4

## Slide 5
Week 1 — W26 · Jun 22–28 · Boost: TikTok
Post all platforms · boost TikTok only · learn Promote mechanics · establish baseline CPV + CPF · Php 2,000
Drop Date
Post / Topic
Platform
Budget
MON · Jun 22
Boost: Jun 23–24
Ang Sabi Nila: Pang-Matalino Lang Iyan
TikTok Promote
Php 350/day × 2
Php 700
WED · Jun 25
Boost: Jun 26–27
Gemini para sa Guro
TikTok Promote
Php 350/day × 2
Php 700
FRI · Jun 27
Boost: Jun 28–29
1 Buwan Kasama Tito AI — Ang Resulta
TikTok Promote
Php 300/day × 2
Php 600
W26 WEEK TOTAL
Php 2,000
HOW TO BOOST ON TIKTOK PROMOTE
1
Open TikTok app → tap the posted video → tap Share (arrow) → tap "Promote"
2
Goal: select "More video views" — views drive the algorithm and bring organic followers
3
Audience: Automatic · Duration: 2 days · Budget: Php 300–350/day · confirm payment
4
Start: morning AFTER posting — let it run organically for 8–12 hours first for best results
Tito AI @TitoAIPH · Content Boost Plan · W26–W28 · June–July 2026
5

## Slide 6
Week 2 — W27 · Jun 29–Jul 5 · Boost: TikTok + IG
Post all platforms · add Instagram Boost · compare cost-per-follow using W26 data · Php 2,000
Drop Date
Post / Topic
Platform
Budget
MON · Jun 30
Boost: Jul 1–2
July Teaser — Ano ang Susunod?
TikTok Promote
Php 700
WED · Jul 2
Boost: Jul 3–4
TBD — Wednesday Demo
Instagram Boost
Php 700
FRI · Jul 4
Boost: Jul 5–6
TBD — Friday Story
TikTok Promote
Php 600
W27 WEEK TOTAL · TikTok Php 1,300 + Instagram Php 700
Php 2,000
TikTok Promote — same as Week 1
1
Goal: Video views · Audience: Automatic
2
Duration: 2 days · Php 350/day for Mon post, Php 300/day for Fri
3
If W26 CPF was < Php 20, increase Mon to Php 400/day
Instagram Boost — NEW this week
1
Open Instagram post → tap "Boost Post" → Goal: More profile visits
2
Audience: Automatic · Duration: 2 days · Php 350/day
3
Check results in Instagram Insights → Boosted post tab after 48 hrs
Tito AI @TitoAIPH · Content Boost Plan · W26–W28 · June–July 2026
6

## Slide 7
Week 3 — W28 · Jul 6–12 · Boost: All 3 Platforms
Post all platforms · full boost push · compare CPF · decide July budget · FB Page required
TikTok Promote
Php 600
MON · Jul 7
TBD — Monday AI Tip
Php 300/day × 2 days
Boost: Jul 8–9
Goal: Video views · Automatic audience · Start Jul 8 morning
Facebook Boost
Php 800
WED · Jul 9
TBD — Wednesday Demo
Php 400/day × 2 days
Boost: Jul 10–11
Goal: Reach + Page likes · Philippines 22–45 · Tech/Freelancing interests
Instagram Boost
Php 600
FRI · Jul 11
TBD — Friday Story
Php 300/day × 2 days
Boost: Jul 12–13
Goal: Profile visits · Automatic audience · Start Jul 12 morning
⚠️ BEFORE WEEK 3: Facebook Page required. Go to facebook.com/pages/create → Business or brand. Personal profiles cannot run paid boosts or access analytics.
W28 TOTAL: Php 2,000 · TikTok Php 600 + Facebook Php 800 + Instagram Php 600 · 3-Week Grand Total: Php 6,000
After W28: compare CPF across all 3 platforms → winner gets biggest July budget. Scale rule: CPF < Php 12 → add Php 400/week to that platform.
Tito AI @TitoAIPH · Content Boost Plan · W26–W28 · June–July 2026
7

## Slide 8
Budget Summary — 3 Weeks
Php 6,000 total · W26 TikTok → W27 TikTok+IG → W28 All 3
Week
TikTok
Instagram
Facebook
W26 Jun 22–28
Php 2,000
3 posts · TikTok Promote only
—
—
W27 Jun 29–Jul 5
Php 1,300
2 posts · TikTok Promote
Php 700
1 post · Instagram Boost
—
W28 Jul 6–12
Php 600
1 post · TikTok Promote
Php 600
1 post · Instagram Boost
Php 800
1 post · Facebook Boost
3-WEEK GRAND TOTAL
Php 3,900
Php 1,300
Php 800
SCALE RULES — WEEK 4+ (July)
Single post earns 25+ followers → extend that post 2 more days at the same daily rate
Cost-per-follow drops below Php 30 → increase that platform's weekly budget by Php 400
Platform with lowest CPF across W26–W28 → gets the biggest share of July budget
Tito AI @TitoAIPH · Content Boost Plan · W26–W28 · June–July 2026
8

## Slide 9
KPIs to Track Weekly
Baseline: IG 1,031 views · 389 reached (organic) · targets based on PH market rates for new accounts
ORGANIC BASELINE (before boost) · Instagram: 1,031 total views · 389 accounts reached · ~200–350 views/Reel · TikTok: pending · New account — boost targets set conservatively
Metric
TikTok
Instagram
Facebook
Reach per boosted post
600–1,500
400–900
500–1,200
Views per boosted post
800–2,000
300–700
N/A
New followers per boost
5–20
3–12
10–25 page likes
Cost per follow
Php 35–90
Php 60–110
Php 35–80
Watch completion (W1)
15–30%
20–35%
N/A
W3 CPF target (goal)
< Php 45
< Php 65
< Php 55
WHERE TO PULL · TikTok: Creator Center → Analytics + Promote tab Instagram: Professional Dashboard → Boosted post Facebook: Business Suite → Page Insights
POST-DAY CHECKLIST
☐ Reply to ALL comments within first 1 hour of posting
☐ Pin first comment within 5 min — tip or claude.ai link
☐ Upload natively to each platform — never use TikTok cross-post link
☐ End every video with a YES/NO question to drive comment rate
Tito AI @TitoAIPH · Content Boost Plan · W26–W28 · June–July 2026
9